## Consultancy Project Dissertatio
Date | Meeting | Section(s) Due | Meeting Objective | Next Steps
Monday 10th May (11am) | Meeting 1 | Student/Supervisor: N/A | Student/Supervisor: Kick-off meeting with introduction, briefly explain company and project area | Student: Speak to company to further understand project and focus scope Supervisor: N/A
Monday 24th June (4 pm) | Meeting 2 | Student/Supervisor: N/A | Student/Supervisor: Meeting to go over focused scope of project and areas on interest | Student: Plan project and set out project management Supervisor: N/A
Monday 5th July (4 pm) | Meeting 3 | Student: Project Management Sheet Supervisor: N/A | Student/Supervisor: Establish Sections of Project and Provisional Mini-Deadlines/Next Steps | Student: Plan (4) Literature Review Supervisor: N/A
Wednesday 14th July (4.30 pm) | Meeting 4 | Student: [Plan] (4) Literature Review Supervisor: N/A | Student: Talk through (4) Literature Review plan at a high level Supervisor: N/A | Student: Complete (4) Literature Review Supervisor: N/A
Monday 19th July (4 pm) | Meeting 5 | Student: (4) Literature Review Supervisor: N/A | Student: Talk through (4) Literature Review plan at a high level Supervisor: N/A | Student: Complete (5) Data, (6) Exploratory Analysis Supervisor: Review (4) Literature Review
Friday 23rd July (10 am) | Meeting 6 | Student: (5) Data, (6) Exploratory Analysis Supervisor: [Comments] (4) Literature Review | Supervisor: Talk through comments on (3) Introduction, (4) Literature Review Student: Talk through (5) Data, (6) Exploratory Analysis at a high level | Student: Complete (7) Modelling, (8) Results Supervisor: Review (5) Data, (6) Exploratory Analysis
Friday 30th July (10 am) | Meeting 7 | Student: (7) Modelling, (8) Results Supervisor: [Comments] (5) Data, (6) Exploratory Analysis | Supervisor: Talk through comments on (5) Data, (6) Exploratory Analysis Student: Talk through (7) Modelling, (8) Results at a high level | Student: Complete (3) Introduction, (9) Conclusion and Limitations Supervisor: Review (7) Modelling, (8) Results
Monday 2nd August (4 pm) | Meeting 8 | Student: (3) Introduction, (9) Conclusion and Limitations Supervisor: [Comments] (7) Modelling, (8) Results | Supervisor: Talk through comments on (7) Modelling, (8) Results Student: Talk through (3) Introduction, (9) Conclusion and Limitations | Student: Complete (1) Abstract, (2) Impact Statement Supervisor: Review (3) Introduction, (9) Conclusion and Limitations
Friday 6th August (10 am) | Meeting 9 | Student: (1) Abstract, (2) Impact Statement Supervisor: [Comments] (3) Introduction, (9) Conclusion and Limitations | Supervisor: Talk through comments on (3) Introduction, (9) Conclusion and Limitations Student: Talk through (1) Abstract, (2) Impact Statement | Student: Incorporate feedback and revise Sections 3 - 9 Supervisor: Review (1) Abstract, (2) Impact Statement
Monday 9th August (4pm) | Meeting 10 | Student: Revised Sections 3 - 8 Supervisor: [Comments] (1) Abstract, (2) Impact Statement | Supervisor: Talk through comments on (1) Abstract, (2) Impact Statement Student: Talk through Revised Sections 3 - 9 at a high level | Student: Incorporate feedback on (1) Abstract, (2) Impact Statement complete document formatting (Cover Page, Contents, Tables, Figures), Bibliography and Appendices Supervisor: N/A
Friday 13th August (10 am) | Meeting 11 | Student: Final Draft Supervisor: N/A | Student: Talk through Final Draft Supervisor: N/A | Student: Incorporate any final feedback from Raju Supervisor: N/A
Monday 16th August (10am) | N/A (FINAL DEADLINE) | Student: Final Draft Supervisor: N/A | Student: N/A Supervisor: N/A | Student: N/A Supervisor: N/A